CEF PORTFOLIO INTELLIGENCE PLATFORM

CEF-PIP

6-WEEK MVP IMPLEMENTATION PLAN

Version 1.0  |  19th June, 2026

# 1. Executive Summary

The objective is a fully functional asset tracking, cashflow visibility and alerting platform, integrated with one live AssetCo by the end of the week six.

The build will use simple, developer-friendly infrastructure — GitHub, Render, Vercel, and Supabase — so that the team can ship quickly. Claude Code will be used as an AI pair-programming assistant throughout to accelerate development and support knowledge transfer during team mentoring.

| Item | Decision |
| --- | --- |
| Delivery timeline | 6 weeks (see Section 4 for week-by-week plan) |
| Primary focus | Cashflow Engine, Default Alerting, Event Ingestion API |
| First live AssetCo | Onboarded by end of Week 6 |
| AI assistant | Claude Code (Anthropic) — coding, review, documentation |
| Infrastructure tier | Free / cheapest tiers only for MVP phase |

# 2. MVP Scope — What We Are Building

The MVP is scoped to the core financial intelligence and alerting functionality. All other modules ( analytics, compliance engine, deployment architecture upgrades) are to be deferred to Phase 2.

## 2.1  In Scope (MVP)

| Module | Description |
| --- | --- |
| Event Ingestion API | POST /api/v1/events endpoint — receives all standardised events from AssetCo platforms with HMAC-SHA256 signature verification |
| Cashflow Engine | Processes payment.received, payment.missed, payment.defaulted events; updates collections totals, outstanding balances, and default status per asset and customer |
| Alert Engine | Triggers notifications on payment.defaulted and asset.fault.detected events; sends email alerts to CEF team |
| Asset Registry | Basic asset ledger tracking CEF-funded assets: ID, AssetCo, status, customer, deployment date, sync metadata |
| Reconciliation Endpoint | Nightly pull via GET /cef/payments, GET /cef/assets, GET /cef/faults to catch missed events |
| CEF-PIP Dashboard | Web dashboard: portfolio cashflow summary, default tracker, active faults, asset status list, alert feed |
| AssetCo Test Harness | Fictional AssetCo integration that emits all standard events — used to validate the full platform end-to-end before live onboarding of the first AssetCo |
| User Auth (basic) | Email + password login with role tagging (Executive, Finance, Ops); Supabase Auth. No SSO in MVP — Entra ID deferred to Phase 2. |

## 2.2  Out of Scope for MVP

- Microsoft Entra ID SSO (deferred to Phase 2)

- Advanced analytics / historical trend engine

- Compliance enforcement engine

- Remote control request flow (Disable/Enable)

- Second and third AssetCo onboarding (Phase 2)

# 3. Technology Stack

All tools are selected for simplicity, free-tier availability, and ease of onboarding for a team new to the codebase. The stack is designed to be understandable without deep DevOps expertise.

## 3.1  Stack Decisions

| Layer | Tool / Service | Role | Tier |
| --- | --- | --- | --- |
| Frontend | Next.js + React | Dashboard UI — server-side rendering, API routes | Free (open source) |
| Frontend Hosting | Vercel | Deploy Next.js app — zero-config, GitHub-integrated | Hobby (Free) |
| Backend API | Node.js + Express | Event Ingestion API, Cashflow Engine, Alert Engine | Free (open source) |
| Backend Hosting | Render | Host Express API as a web service — auto-deploys from GitHub | Free tier (spin-down on idle) |
| Database | Supabase (PostgreSQL) | Primary data store — assets, payments, events, faults, users | Free tier (500 MB, 2 projects) |
| Authentication | Supabase Auth | Email/password login, JWT session management, row-level security | Free (included) |
| Email Alerts | Resend | Transactional email for default / fault notifications | Free (100 emails/day) |
| Background Jobs | Render Cron Jobs | Nightly reconciliation scheduler — pull-based fallback | Free tier |
| Source Control | GitHub | All code, CI/CD trigger, project board for task tracking | Free |
| CI/CD | GitHub Actions | Auto-test and deploy on every push to main | Free (2,000 min/mo) |
| AI Assistant | Claude Code | AI pair-programming: code generation, review, documentation, debugging | Pro plan (~$20/mo per person) |
| Secret Management | Render Env Vars + .env.local | API keys, DB URLs, HMAC secrets — never committed to Git | Free |
| API Testing | Postman / Thunder Client | Test event endpoints during development | Free |

Render free tier spins down after 15 minutes of inactivity. This is acceptable for MVP/testing. Upgrade to Render Starter ($7/mo) before live AssetCo onboarding to ensure always-on availability.

## 3.2  Repository Structure

One GitHub organisation, two repositories:

- cef-pip-api — Express backend (Event Ingestion, Cashflow Engine, Alert Engine, Reconciliation)

- cef-pip-dashboard — Next.js frontend (all dashboard views)

Both repos connect to the same Supabase project. GitHub Actions deploys automatically on push to main.

# 4. Six-Week Implementation Plan

## Week 1 — Foundations & Event Ingestion API

| Task | Output |
| --- | --- |
| Project kick-off: brief team, set up GitHub org, repos, Vercel, Render, Supabase accounts. Install Claude Code. Define coding conventions. | All accounts active, repos live |
| Design and document database schema (assets, customers, events, payments, faults, users tables). Review with team. | Schema documented in GitHub wiki |
| Set up Supabase project — create tables, run migrations, configure Row-Level Security policies. | DB live with seed data |
| Scaffold Express API project — folder structure, middleware (auth, error handling, logging), health-check endpoint. | GET /health returning 200 |
| Build POST /api/v1/events endpoint: parse payload, verify HMAC-SHA256 signature, validate schema, insert to events table, return 200/400. | Events endpoint accepting payloads |
| Write unit tests for event ingestion (Jest). Set up GitHub Actions CI — run tests on every push. | Green CI pipeline |
| Team review + retrospective. Claude Code code review session. | Week 1 concludes |

## Week 2 — Cashflow Engine & Alert Engine

| Task | Output |
| --- | --- |
| Build Cashflow Engine: event handler for payment.received — update collections total, clear missed-payment flag, recalculate outstanding balance per asset. | payment.received processed correctly |
| Build payment.missed handler — mark customer overdue, increment missed_count, start default timer. | Missed payment state tracked |
| Build payment.defaulted handler — flag asset/customer as defaulted, trigger Alert Engine, log to audit table. | Default flagged in DB |
| Build Alert Engine: on default/fault event, compose and send email via Resend to configured CEF recipients. | Email arriving on test default |
| Build asset.fault.detected and asset.fault.resolved handlers in Cashflow + Alert engines. | Fault lifecycle tracked end-to-end |
| Integration tests — fire a sequence of events (deploy → payment × 3 → miss → default → fault) and verify all DB state and email alerts are correct. | Integration test suite passing |
| Claude Code review — all engines. Retrospective. | Week 2 concludes |

## Week 3 — Dashboard (Frontend)

| Task | Output |
| --- | --- |
| Scaffold Next.js project — folder structure, Tailwind CSS, Supabase client, environment variables. Deploy blank app to Vercel. | Blank dashboard live on Vercel |
| Build authentication flow: login page → Supabase Auth → JWT → role-based redirect (executive / finance / ops views). | Login + auth working |
| Build Portfolio Dashboard page: cashflow summary cards (total collected, outstanding, default rate), recent alerts feed, data freshness indicator. | Portfolio view rendering live data |
| Build AssetCo Dashboard page: per-AssetCo cashflow table, customer status breakdown, fault count, active assets count. | AssetCo view working |
| Build Individual Asset page: asset identity card, payment history table, operational status, fault log. | Asset detail page working |
| Wire all pages to real API/DB data. Fix any data-shape mismatches. Basic responsive layout check. | Full dashboard reading live data |

## Week 4 — Asset Registry & Reconciliation

| Task | Output |
| --- | --- |
| Build Asset Registry module: asset.created, asset.deployed, asset.decommissioned event handlers — maintain authoritative asset ledger in DB. | Asset registry tracking state |
| Build GET /cef/assets, GET /cef/payments, GET /cef/faults endpoints (the pull-based reconciliation endpoints that AssetCo platforms must expose — CEF-PIP will call their equivalent). | Reconciliation query endpoints live |
| Build Reconciliation Service: scheduled job (Render Cron) — calls AssetCo REST endpoints, compares with local data, flags discrepancies, logs results. | Nightly reconciliation job running |
| Expose sync.heartbeat event handling — track lastSyncedAt per AssetCo, flag stale integrations on dashboard. | Heartbeat tracking live |
| Add asset registry UI to dashboard — asset list view with status, last sync, default/fault indicators. Week 4 retrospective. | Asset list visible in dashboard |

## Week 5 — Fictional AssetCo Onboarding & End-to-End Testing

| Task | Output |
| --- | --- |
| Build "DemoSolar" test harness — a small script (Node.js) that simulates a real AssetCo platform. It emits all 14 standard event types to CEF-PIP's Event Ingestion API with valid HMAC signatures, realistic payload data, and configurable scenarios (on-time payments, defaults, faults, recoveries). | DemoSolar script running against staging |
| Run full end-to-end scenario: onboard DemoSolar → deploy 10 assets → simulate 3 months of payments → trigger 2 defaults → trigger 1 fault → resolve fault → run reconciliation. Verify all states in the dashboard and alert emails. | Full lifecycle validated |
| Fix all bugs found in E2E run. Performance check — ensure dashboard loads in under 3 seconds on free-tier DB. | Bug-fix release |
| User acceptance testing: Team access the staging dashboard. Collect feedback. | UAT sign-off or change list |
| Implement UAT feedback (cosmetic/usability issues). Write AssetCo Integration Guide (how to send events, endpoint URLs, HMAC signing, required event types). | Integration Guide v1.0 published |

## Week 6 — First Live AssetCo Onboarding & Handover

| Task | Output |
| --- | --- |
| Kick-off with first live AssetCo technical team. Share Integration Guide. Provision API key + HMAC secret for their platform. Walk them through the event payload structure. | AssetCo onboarded with credentials |
| Upgrade Render backend from free tier to Starter ($7/mo) for always-on availability. Run final production deployment checklist. | Production environment stable |
| AssetCo team implements webhook push to CEF-PIP Event Ingestion API (their development effort). CEF team available for support. Verify first real events arriving. | First real events in production DB |
| Monitor live data flow — verify cashflow figures, confirm alerts triggering, run first real reconciliation against AssetCo REST endpoints. | Live cashflow data visible in dashboard |
| Final Team demo: live dashboard showing real AssetCo data, default alerts, asset registry. | sign-off |
| Retrospective, lessons learned. Draft Phase 2 scope (Entra ID, analytics, second AssetCo, compliance engine). Hand off operational runbook to team. | MVP delivered. Phase 2 plan initiated. |

# 5. Cost Estimate — MVP Phase (Monthly)

## 5.1  Infrastructure & Services

| Service | Plan | What It Covers | Est. Monthly Cost (USD) |
| --- | --- | --- | --- |
| Vercel | Hobby (Free) | Dashboard hosting, unlimited personal projects, 100 GB bandwidth | $0 |
| Render — Web Service | Free tier → Starter from Week 6 | Backend API hosting. Free tier spins down; upgrade before live onboarding. | $0 → $7 |
| Render — Cron Job | Free tier | Nightly reconciliation job scheduler | $0 |
| Supabase | Free tier | PostgreSQL DB (500 MB), Auth, Row-Level Security, 2 GB bandwidth | $0 |
| Resend | Free tier | 100 transactional emails/day (alerts, notifications) | $0 |
| GitHub | Free (org) | Repos, GitHub Actions CI/CD (2,000 min/mo included) | $0 |

## 5.2  AI Development Assistant

| Tool | Plan | What It Covers | Est. Monthly Cost (USD) |
| --- | --- | --- | --- |
| Claude Code | Pro plan | AI pair-programming in terminal — code generation, debugging, documentation, code review, test writing. Used by lead and developers throughout the 6-week build. | ~$20/month per team member |

Claude Code Max is the recommended tier for professional development use. Providing higher usage limits suited to active daily coding across multiple team members.

## 5.3  Total MVP Infrastructure Cost Summary

| Category | Monthly Cost (USD) | Notes |
| --- | --- | --- |
| Cloud Infrastructure (Weeks 1–5) | $0 / month | Entirely on free tiers during development |
| Cloud Infrastructure (Week 6+ live) | $7 / month | Render Starter for always-on backend |
| AI Assistant (Claude Code) | ~$20/month per team member | Primary development accelerator — recommended throughout build |
| TOTAL (MVP monthly, live) | <$100 | Trivial vs. external dev cost. |

A typical external development team for a project of this scope would cost at least $30,000. The in-house build with Claude Code as an accelerator delivers the same outcome at a fraction of the cost, while keeping all IP and institutional knowledge within.

# 6. Team Structure & Mentorship Approach

## 6.1 Mentorship & Claude Code Integration

Project lead will use daily structured touchpoints to keep the team moving and learning:

- Daily 15-minute stand-up: what did you build, what's blocking you, what's next.

- Pair programming sessions each morning using Claude Code — the lead codes alongside each person, explain patterns, and review logic in real time.

- End-of-week code review sessions: the team walks through the week's PRs together. Claude Code is used to explain any patterns the team found confusing.

- Living documentation: all architectural decisions, API contracts, and setup instructions are written in the GitHub wiki as we go, with Claude Code used to draft technical docs quickly.

- No 'black box' rule: if Claude Code writes a piece of code, the developer must be able to explain every line before it merges. This builds genuine understanding, not dependency.

Claude Code is a force-multiplier, not a replacement for understanding. Every team member will come out of this project with hands-on experience building a production API, a React dashboard, and a real integration workflow — skills that directly serve Fundco going forward.

# 7. Risks & Mitigations

| Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- |
| AssetCo tech team slow to implement their side of the integration | Medium | High | Week 5 Integration Guide delivered early. Lead available to answer questions. DemoSolar test harness can stand in if AssetCo misses Week 6 deadline. |
| Free tier Render spin-down causes missed events during development | High | Low | Expected — acceptable during development. Upgrade to Starter ($7/mo) before live onboarding in Week 6. |
| Supabase free tier storage (500 MB) exceeded | Low | Medium | MVP data volume is small. Monitor via Supabase dashboard. Pro plan ($25/mo) available if needed. |
| Team member unavailable for a week | Low | Medium | Claude Code reduces per-developer bottleneck. Lead can cover critical path items. Scope reduced to match capacity. |
| Scope creep — stakeholder requests additional features during build | Medium | High | Strict MVP scope document shared from Day 1. All additions logged for Phase 2. |
| HMAC signing implementation errors causing rejected events | Medium | Medium | DemoSolar test harness validates signing logic in Week 5 before any live AssetCo is onboarded. |

# 8. Definition of Done — MVP

The MVP is complete when all of the following are true:

- CEF staff can log in to the dashboard and see real cashflow data from at least one live AssetCo.

- Payment defaults automatically trigger email alerts to the CEF team within 5 minutes of the event.

- Asset cash flows, errors etc are visible on the dashboard within 5 minutes of the event being pushed.

- The nightly reconciliation job runs successfully and flags any events missed during the day.

- The Asset Registry shows all CEF-funded assets with correct status and last-sync timestamp.

- DemoSolar test harness has been run to full scenario completion with no data errors.

- The first live AssetCo has pushed at least one real payment.received event that appears correctly in the dashboard.

- An AssetCo Integration Guide exists and has been validated by the live AssetCo development team.

- All code is on GitHub with passing CI tests and documented for future use .

# 9. Phase 2 Preview (Post-MVP)

Phase 2 is not scoped in this document but is noted here so the stakeholders understand what comes next. All items below are explicitly deferred from the MVP.

| Phase 2 Item | When |
| --- | --- |
| Microsoft Entra ID SSO (replace email/password login) | Immediately post-MVP |
| Second and third AssetCo onboarding (EML, SSM) | Month 2–3 |
| Advanced analytics — historical trends, ROI curves, cohort analysis | Month 2–3 |
| Compliance enforcement engine — SLA breach alerts, non-submission flagging | Month 3 |
| Remote control request flow (Disable/Enable with dual approval) | Month 3–4 |
| Infrastructure migration — Azure, Docker, Kubernetes, Azure API Management | Month 4–6 |
| External auditor read-only access | Month 4 |

CEF-PIP MVP Implementation Plan